## Sheet1
Phase | Status | Responsible Member | Deliverables | Deadline
Phase 1 - Kafka Producer for Reddit API data ingestion | Completed | Basim | Reddit API data ingestion via Kafka producer | 2025-11-03
Phase 2 - Confluent Cloud setup and configuration | Completed | Basim | Confluent Cloud environment configured and connected | 2025-11-07
Phase 3 - Kafka Consumer with sentiment analysis integration | In Progress | Aasim | Consumer reads from Kafka and applies sentiment analysis | 2025-11-10
Phase 4 - MongoDB Atlas connection and data storage | In Progress | Both | Processed data stored in MongoDB Atlas | 2025-11-14
Phase 5 - Streamlit dashboard for data visualization | In Progress | Aasim | Streamlit dashboard displaying live sentiment insights | 2025-11-17
Phase 6 - Testing, documentation, and final deployment | In Progress | Both | End-to-end testing, documentation, and deployment | 2025-11-24